## Slide 1
TRAP
TRANSBOUNDARY AIR POLLUTION HEALTH INDEX DEVELOPMENT AND IMPLEMENTATION
3rd Steering Committee Meeting
Municipality of Florina
Marina Proikaki
Regional Development Consultant, LEVER S.A
16/10/2019/3rd Steering Committee Meeting
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 2: GROUP OF IMPLEMENTED ACTIVITIES / TENDERS
External Expertise and Services | TENDERS/ ΑCTIVITIES | BUDGET A.P | CONTRACTED BUDJET | PAID BUDJET | VERIFIED BUDJET
WP1 – Project Management and Coordination | Del.1.2.2 Project Management Guide | 500 € | 500 € | 500 € August 2019 | x
WP1 – Project Management and Coordination | Del.1.2.3 Steering Committee Meetings | 1.500 € | 1.500 € | 300 € August 2019 | x
WP2 – Communication and Dissemination | Del. 2.2.1 Communication Plan | 3.000 € | 3.000 € | 3.000 € August 2019 | X
WP2 – Communication and Dissemination | Del.2.2.2 Project Identity | 1.000 € | 1.000 € | 1.000 € August 2019 | X
WP2 – Communication and Dissemination | Del.2.2.3 Promotional Material | 3.000 € | 1.500 € | 1.500 € August 2019 | X
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 3: GROUP OF ACTIVITIES / TENDERS
External Expertise and Services | TENDERS/ ΑCTIVITIES | BUDGET A.P | CONTRACTED BUDJET | PAID BUDJET | VERIFIED BUDJET
WP1 – Project Management and Coordination | Del. 1.2.4 Progress Reports | 7.000 € | 7.000 € | x | x
WP2 – Communication and Dissemination | Del.2.2.4 Layman Report | 2.000 € | 2.000 € | x | x
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 4: NEXT STEPS/ TENDERS REMAINING
External Expertise and Services | TENDERS/ ΑCTIVITIES | COST | Checkx
WP1 WP2 WP6 | Event organising: Organisation of 1SC (WP1) Organisation of Final Conference (WP2) Organisation of 1 Workshop (WP6) | 5.500,00€ | By the end of 2019
WP4 WP5 WP6 | Monitoring process: Record measurements from the stations (WP4) Evaluate periodic measurement and create periodical evaluation data reports (WP4) Creation of an online Tool for Air Quality and Health Indicators (WP5) Contribute to partnership joint study for comparative analysis (WP6) Implementation of health sensitization campaigns to schools and health operators (WP6) Preparation promotional material for health sensitization campaigns to schools and health operators (WP6) | 19.300,00€ | By the end of 2019
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 5: GROUP OF ACTIVITIES / TENDERS- REMAINING
External Expertise and Services | TENDERS/ ΑCTIVITIES | COST | Checkx
WP4- Air Monitoring Mechanism (equipment) | Air Monitoring Equipment : Equipment: Air Quality Monitoring Station and measurement devises, sensors | 100.000,00€ | By the end of 2019
124.800,00 €
Assignment of Auditor
Verification of expenditures

## Slide 6
Thank you!
https://trap-project.eu/
16/10/2019/3RD STEERING COMMITTEE MEETING