## Slide 1
TRAP
TRANSBOUNDARY AIR POLLUTION HEALTH INDEX DEVELOPMENT AND IMPLEMENTATION
Theodoros Stavrakas
Environmental Centre of Western Macedonia
16 - 10 - 2019 / [Thessaloniki/3rd SC Meeting]
3rd Steering Committee Meeting
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 2
The project is co-funded by the European Union and by National Funds of the participating countries
TRAP
“Transboundary Air Pollution Health Index Development and Implementation”
which is co-funded by the Interreg IPA Cross-Border Cooperation Programme
Greece – The former Yugoslav Republic of Macedonia 2014-2020
MIS Code: 5032912
Priority Axes: 2. Protection of Environment – Transportation
Thematic Priority: 2b. Protecting the environment and promoting climate change adaptation and mitigation, risk prevention and management
Specific Objective: 2.3 Sustainable management of protected areas, ecosystems and biodiversity

## Slide 3
The project is co-funded by the European Union and by National Funds of the participating countries
Project Duration: 24 months 03-08-2018 until 03-08-2020
Total Budget: 969.331,00€
Union Support: 823.931,35€
National Funding: 145.399,65€
Equipment: 430.000,00€
Strategic objective of TRAP project is the creation of an ICT application integrating Air Quality Monitoring with Air Pollution Health Indicator (APHI) in CB area.
The specific sub-objectives of the project are to:
• Develop and evaluate emission inventories
• Assess the health risk related to air quality measurements
• Create integrated ICT tool including air quality information correlated to possible health impacts
• Evaluate the CB conditions regarding air quality and transported pollution in CB area
• Engage relevant stakeholders in order to inform them on the created tool operation and indexes
• Disseminate and communicate the project results to key stakeholders, general public and vulnerable groups.

## Slide 4: WP1: PROJECT MANAGEMENT AND COORDINATION
The project is co-funded by the European Union and by National Funds of the participating countries
1.2 Project Management Guide: Finished June 2019
1.3 Steering Committee Meetings:
3 SCM organized by ERFC 16/10/2019 Thessaloniki
4th SCM will be organized by CCC. February 2020 according to activity file (if possible together with workshop or sensitization campaign in order all partners to be present
1.4 Progress Reports:
Submitted 2 PR – Partners use the same template renewing the financial data in order to keep record with Contracted budget and total expenditure paid out columns
Next reporting probably through MIS system January 2020 (by LP, partners will send LP the excel file).

## Slide 5: WP1: PROJECT MANAGEMENT AND COORDINATION
The project is co-funded by the European Union and by National Funds of the participating countries
1.5 IPA Audit: Partners proceed to expenses certification (KEPE under certification 35.000€ until 30-8-2019).
Administrative – Finance:
Contracted external expert 55.500€
Program Name officially changed search following days through COM officer Mrs E. Votsari official logo for usage
Will announce equipment tender within November 2019
Pre-financing of IPA partners PB4_CCC received 2nd Payment
Request will be made within 2019 for project modification and extension of duration (Partners prepare budget changes if anything)

## Slide 6: WP2: COMMUNICATION AND DISSEMINATION
The project is co-funded by the European Union and by National Funds of the participating countries
2.1 Communication Plan: Finalized May 2019
2.2 Project identity:
Project website operational (all partners please upload deliverables and invitations, agenda, photo, videos if possible from communication and dissemination actions)
2 FB pages operational (all partners please upload deliverables and invitations, agenda, photo, videos if possible from communication and dissemination actions)
1st Newsletter must be prepared by MoF and Lever for Greek partners
2.3 Promotion Material
PB2 - MoF must print promotional material for Greek partners, layout created by Lever
PB4 – CCC must print promotional material for North Macedonia partners, layout created by Lever
2.4 Layman Reports
1st Layman Report must be prepared by MoF and Lever for Greek partners
2.5 Final Conference: Not yet
NOTICE: Program Name officially changed search following days through COM officer Mrs E. Votsari official logo

## Slide 7: WP3: AIR QUALITY IMPACT ASSESMENT
The project is co-funded by the European Union and by National Funds of the participating countries
3.1 Identification of the emission sources (2/country):
ERFC finalized
KEPE to be finalized within November 2019
3.2 Development of regional emission inventory (1/country)
KEPE and ERFC for Greek partners begin within November 2019
3.3 Contribution assessment of emissions (2/country)
To be discussed by partners / January 2020 according to excel activity file
3.4 Development of air quality plan (2/country)
To be discussed by partners / April 2020 according to excel activity file

## Slide 8: WP4: AIR MONITORING MECHANISM
The project is co-funded by the European Union and by National Funds of the participating countries
4.1 Specifications of monitoring equipment:
Finalized send to PB2 also
4.2 Tender Procedures
Within November 2019
4.3 Installation of the stations
Within 2019
4.4 Measurements
January 2020
4.5 Monitoring data validation and analysis
Begin January 2020

## Slide 9: WP5: PUBLIC HEALTH IMPACTS AND INDEX
The project is co-funded by the European Union and by National Funds of the participating countries
5.1 Assessment of basic health profile
To be discussed by partners / Contents in June 2020 according to excel activity file
5.2 Air Quality and Health Risk assessment
To be discussed by partners / Contents in June 2020 according to excel activity file
5.3 ICT Tool for Air Quality and Health Indicators
To be discussed by partners / Issue for the 3rd SCM according to excel activity file
5.4 Air Quality Public Health Index
To be discussed by partners / Issue for the 3rd SCM according to excel activity file

## Slide 10: WP6: CROSS BORDER NETWORKING
The project is co-funded by the European Union and by National Funds of the participating countries
6.1 Joint comparative analyses on Air Quality
To be discussed by partners / Issue for the 4th SCM according to excel activity file
6.2 Training workshops on Air Quality and Health
To be discussed by partners / Issue for the 4th SCM according to excel activity file
Partners PB2, PB3 and PB4, responsible for workshops, creation of workshop material and organization of sensitization campaigns must start preparing the material including videos, presentations etc according to AF and JoB.
PB2 – Municipality of Florina must as soon as possible to determine external expert in order to participate to sensitization campaign and workshop
6.3 Air Quality and Health sensitization campaigns
To be discussed by partners / Issue for the 4th SCM according to excel activity file
ERFC organizing at 17th of October 2019 (tomorrow 2nd sensitization activity Experts roundtable)
PB2 – Municipality of Florina must as soon as possible to determine external expert in order to participate to sensitization campaign and workshop

## Slide 11: JS/MA COMMENTS BY MR GEORGE PAPAPOSTOLOU (GPAPAPOSTOLOU@MOU.GR):
The project is co-funded by the European Union and by National Funds of the participating countries
Positive comments for project implementation, favorable for TRAP 2 under new call under discussion the scheme and the topic.
Total Expenditures paid until 30-6-2019 according to 2nd PR out 92.015,68€.
Zero spending by PP2 and only 6.426,14€ by PP5 must harry their tenders and declare expenditures to next reporting period until 30th of June 2019.
Examine the need for signing Memorandum of Collaboration or Understanding for air quality data and measurements of cross border stations.
Problem with borderline and name under common map is solved, program name officially changed we wait for confirmation.
Requesting modification within 2019 (December), partners should identify any budget changes needed. Expansion for 6months. (JS will support request).
Probability to gain extra budget for WP6 for common sensitization activities with other health project, project identified is “HEALTH-INFO” http://www.healthinfoproject.eu/

## Slide 12
Contact details: Environmental Centre (ΚΕ.ΠΕ)
Website: www.kepekozani.gr
E-mail: research-studies@kepekozani.gr / info@kepekozani.gr
Fax - Tel. : 0030 2463053666
[LOGO OF PARTNER]
Thank you!
https://trap-project.eu/
https://www.facebook.com/TRAPproject/
https://www.facebook.com/ProjectTRAPpage/