## Slide 1: CENTER FOR CLIMATE CHANGE PP4
www.ckp.org.mk

## Slide 2: EXPENSES
Total expenditures until 30th of September – 40.100,13 €
Chart: 
| FLC 1 | FLC 2
 | 19549.17 | 20550.9556
Both FLCs are approved
Reporting period
FLC 1 – 03.08 – 31.12.2018
FLC 2 – 01.01. – 10.07.2019

## Slide 3
CURRENT BALLANCE
Advance payment- 25.776,25 €
FLC 1
EU payment 11.896,14 € – received on 22.07.2019
MLS payment 2.932,63 €– received on 22.05.2019
Received – 40.578,02 €
Spent – 40.100,13 €
Balance - +477,89 €

## Slide 4
CURRENT BALLANCE
Chart: 
| Spent | Remaining to spent
 | 0.26447 | 0.73395

## Slide 5: PROCUREMENT PLAN
Tender | WP | Deliverable | Description and budget | Status
TD 01 | 3 | 3.4.1 and 3.4.2 | Identification of emission sources and developing regional emission inventory, 10.200 EUR | Procured
TD 02 | 3 | 3.4.3 | Conducting assessment of the contribution of each emission source, 5000 EUR | April 2020
TD 03 | 3 | 3.4.4 | Preparation of the Air Quality Plan for Bitola, 6290 EUR | Oct.-Nov. 2019
TD 04 | 4 | 4.4.4 4.4.5 | Collecting samples from Bitola monitoring station and preparing report from gathered data from monitoring stations (both Gevgelija and Bitola), 9950 EUR | Jan-Feb. 2020
TD 05 | 5 | 5.4.1 5.4.2 | “Assessment of basic profile and conducting air quality and health risk assessment”, 28.900 EUR | Procured
TD 06 | 5 | 5.4.3 | Developing ICT tool, 8500 EUR | Oct.-Nov. 2019
TD 07 | 5 | 5.4.4 | Preparation of the Air Quality Public Health Index, 10.200 EUR | Nov. – Dec. 2019
TD 08 | 6 | 6.4.1 | Joint study for comparative analysis for the CBC area, 6800 EUR | April 2020
TD 09 | 6 | 6.4.2 | Organization of meetings, final conference and training workshops on air quality and health, 9900 EUR | Procured
TD 10 | 6 | 6.4.3 | Air quality and health sensitization campaigns with preparation of Layman reports, 10.000 EUR | Procured

## Slide 6: CURRENT ACTIVITES
Work package | Name of WP | Deliverables | Status
WP 3 | Air Quality Impact Assessment | 3.4.1 – Identification of Emission Sources | Data collected; Report of identification of emission sources – 1st draft ready
WP 3 | Air Quality Impact Assessment | 3.4.2 – Developing regional emission inventory | Based on del. 3.4.1 regional inventory is prepared and finalization of the report is ongoing
WP 5 | Public Health Impact and Index | 5.4.1 - Assessment of basic health profile | Assessment of basic profile, air quality and health risk – 1st draft ready
WP 5 | Public Health Impact and Index | 5.4.2 - Air Quality and Health Risk Assessment | Air Quality and Health Risk Assessment - ongoing
WP 6 | Cross Border Networking | 6.4.3 Air Quality and Health sensitization campaings | - Conducting sensitization activities in Gevgelija and throughout the FB fun page - Sensitization activities in Bitola planned for November 2019 - Stakeholder Involvement Plan – finalized

## Slide 7
COMPLETED ACTIVITES
Eco parade in Gevgelija with kindergardens and schools, 5th of June 2019
Stakeholder information meeting in Gevgelija, 18.06.2019
Stakeholder information meeting in Bitola, 24.09.2019

## Slide 8: PLANNED ACTIVITIES
Work package | Name of WP | Deliverables | Planned
WP 3 | Air Quality Impact Assessment | 3.4.1 - Identification of Emission Sources 3.4.2 – Development of regional emission inventory 3.4.4 - Air Quality Plan for Bitola | Finalization and publication – October 2019 - December 2019 Dec. 2019- April 2020
WP 5 | Public Health Impact and Index | 5.4.1 - Assessment of basic health profile 5.4.2 - Air Quality and Health Risk assessment | Finalization and publication – December 2019/ January 2020
WP 6 | Cross Border Networking | 6.4.3 Air Quality and Health sensitization campaings | Sensitization campaign in Bitola October/November 2019
WP 6 | Cross Border Networking | Conducting trainings for (environment) air quality and health | February – May 2020

## Slide 9: THANK YOU
Web:
www.ckp.org.mk
Email: centarzaklimatskipromeni@yahoo.com