## Slide 1
Ministry of Environment and Physical Planning (MoEPP) – PP5
Thessaloniki, Republic of Greece
16.10.2019
Svetlana Gjorgjeva, Head of department
Aneta Stefanovska, Head of unit
TRAP SC meeting

## Slide 2
Project activities
Preparation and participation to the Steering Committee Meetings
Preparation of the progress reports
Contribution in identification of emission sources and developing regional emission inventory for South east region
Contribution to assessment of basic health profile and preparation of the Air Quality Health Risk Assessment for Bitola and Gevgelija, including participation at all public events organized for these deliverables in Bitola and Gevgelija

## Slide 3
Project activities
Assisting at preparatory activities for developing the Air Quality Public Health Index
Contribution to the communication activities within Air quality and health sensitization campaign
Contribution to preparatory activities for preparation of TOR and opening the tender procedures
And other administration activities

## Slide 4
21.03.2019, Skype meeting with all project partners
06.09.2019, meeting with the manager of Maneko Solutions for implementation of the activities under TD01
Regular coordination meetings with CCC (on daily and week basis) including coordination with other partners
Coordination meetings

## Slide 5
Procurement activities status
Tender No | Name of the tender | WP / Deliverable | Budget | Status
TD01 | External expertise for preparation of technical specification of monitoring equipment and external expertise for preparation of tender procedure for procurement of monitoring station for Gevgelija and upgrade of the monitoring station in Bitola | 4.5.1 and 4.5.2 | 4.200 Euro | Signed contract on 5th September 2019 Period of implementation, 1 month Market analysis, technical specification and complete tender dossier prepared Completed activities within this tender
TD03 | Procurement of monitoring equipment for air quality measurements | 4.5.3 | 250.000 Euro | TD prepared within TD01 Planned to be opened until end of October 2019

## Slide 6
Procurement activities status
Tender No | Name of the tender | Deliverable | Budget | Status
TD02 | Engaging external expertise for conducting survey for emissions for households heating and development of air quality plan | 3.5.2 and 3.5.4 | 5380 Euro | Opened Deadline for submitting offers is 18 October 2019 Period of implementation is 6 months Contract should be sign in November
TD04 | External expertise for analysis of the filters in the accredited chemical laboratory, including 1 year measuring campaign and collection of the samples | 4.5.4 | 50.000 Euro | No activities yet Planned to be opened after installation of the monitoring equipment

## Slide 7
Finances
Category | Spent in EUR until now | Pre-financing received
Staff costs | 8018.32 | 56,497,85
Organization of SC meeting (conference room and catering) | 323 | 
Office and administration | 23.06 | 
Bank charges | 16.26 | 
Daily allowance for SCM | 62 | 
Total | 8442.64 | 

## Slide 8
FLC after finalizing the payment for TD01
Opening tender procedure for TD03 Procurement of monitoring equipment for air quality measurements and installation of the equipment in Gevgelija and Bitola
Engaging consultant (TD 02) and support in the activities for conducting survey for emissions for households heating and develop specific part of a featured Air quality
Contribution to preparation of deliverable for contribution of each emission source
Contribution of project staff to preparation of Layman report and other communication activities within Air and Health Sensitization Campaign
Contribution to conducting trainings for relevant institutions for environment and health
Planned activities for the next period

## Slide 9
Thank you!
CONTACT US
Web: | www.moepp.gov.mk
Portal: | http://air.moepp.gov.mk
Email: | S.Gjorgjeva@moepp.gov.mk, A.Stefanovska@moepp.gov.mk