## Slide 1
TRAP
TRANSBOUNDARY AIR POLLUTION HEALTH INDEX DEVELOPMENT AND IMPLEMENTATION
Progress in project activities
Antonis Bourdalas
Environmental Pr.M.
16.10.2019/ 3rd Steering Committee Meeting, Thessaloniki
Notes: Interreg IPA CBC Programme "Greece - Albania 2014 - 2020"

## Slide 2: PARTNERSHIP

## Slide 3: PP3 - ERFC
E.R.F.C.s’ strategy is to act as an active neutral coordination body that can facilitate the creation of local, regional, national and international platforms where public organizations, business communities academic organizations and civil society can cooperate strategically in an effort to stimulate regional and national growth participating actively in bottom up European Integration.

## Slide 4: EXPENDITURES
 | Until May 2019 | June | July | August | September | Total until September | October | November | December | Forecast October to December
STAFF | 17453.36 | 2533.6 | 3010.01 | 2006.76 | 3010.14 | 28013.87 | 3153.48 | 3010.14 | 2866.8 | 9030.42
TRAVEL | 429.5 |  |  |  |  | 429.5 |  |  |  | 0
EXTERNAL |  |  |  |  |  | 0 | 25000 (8/10/2019) |  | 20000 | 20000
ADMIN |  |  |  |  |  | 584 |  |  |  | 125

## Slide 5: OTHER FINANCIAL ISSUES – AUDITOR SELECTION
The contract with the external expert has been signed (25000 euros have been paid)
Ms Kokosiouli Athina will be the auditor of ERFC (has been selected)
We have already started to uploading the expenses to the MIS Platform and they will be certified by the end of November

## Slide 6: TECHNICAL REPORT REPORTING PERIOD: 01/01/2019 - 30/06/2019
The following deliverables or actions have been completed:
Contribution to the Project Management Guide [Del. 1.2]
Participation in the 2nd SC Meeting and organisation of 3rd SC Meeting [Del.1.3]
Finalization of the 2nd Progress Report [Del. 1.4]
Engagement in the finalization of Communication Plan [Del. 2.1]
Contribution to the content of the official website (Project Identity) [Del. 2.2]
Contribution to the Promotional Material [Del. 2.3]
Finalization of the identification of the emission sources [Del. 3.1]
Dissemination activities VIA Social Media & Sensitization meetings with DIADYMA S.A. and ANKO [Del. 6.3]

## Slide 7: TECHNICAL REPORT REPORTING PERIOD: 01/01/2019 - 30/06/2019

## Slide 8: TECHNICAL REPORT REPORTING PERIOD: 01/01/2019 - 30/06/2019
Preparation activities that have been made:
Development of regional emission inventory [Del. 3.2]
Contribution assessment of emissions [Del. 3.3]
Development of air quality plans [Del. 3.4]
Assessment of basic health profile [Del. 5.1]
Air quality and Health Risk assessment [Del. 5.2]
ICT Tool [Del. 5.3] & Joint comparative analyses on Air Quality [Del. 6.1]

## Slide 9: PROGRESS IN THE IMPLEMENTATION (DEL. 3.2)

## Slide 10: PROGRESS IN THE IMPLEMENTATION (DEL. 5.1)

## Slide 11: PROGRESS IN THE IMPLEMENTATION (DEL. 6.3 / SENSITIZATION MATERIAL)

## Slide 12: NEXT REPORTING PERIOD : 01/07/2019 - 31/12/2019
Next Steps:
Continue implementing
Del. 3.2, Del. 3.3, Del 3.4,
Del, 5.1, Del. 5.2, Del. 5.3,
Del 6.1 and Del. 6.3
Start preparing
Layman Report [Del. 2.4]
Air Quality Public Health Index [Del. 5.4]
Training workshop on Air Quality and Health [Del. 6.2]

## Slide 13: NEXT REPORTING PERIOD : 01/07/2019 - 31/12/2019

## Slide 14
BOURDALAS ANTONIS / bourdalas@erfc.gr
[LOGO OF PARTNER]
Thank you!
https://trap-project.eu/